## TiraBeauty Test Plan
TEST PLAN FOR EBAY |  | SauceDemo
Sr. No | Module Name | Features to be Tested | Features Not Tested | Approach | Pass/Fail Criteria | Suspension Criteria | Environment | Responsibility | Schedule | Risk/Contingency | Approval
1 | Login Page | - Valid login with standard_user | Account lock/unlock, password reset, multi-factor authentication | Automation Testing (Selenium + TestNG) | Pass if all user types accept or reject with correct messages and UI behavior | Testing paused if login form or essential fields are missing | Windows 10/11, Chrome, Firefox, Edge | Hemant Bhase | TBD | No risk | Vaishali Sonanis
- Locked out user error
- Problem user login
- Performance glitch user login
- Error user login
- Visual user login
- Blank username field
- Blank password field
- Valid/Invalid password error message
- Password masking
- Login button enabled/disabled states
2 | Inventory Page | Product tiles: Image, Name, Price, Description, Add to Cart Button | Pagination, User Reviews | Automation Testing (Selenium + TestNG) | Pass if all product elements load & interact correctly | Testing paused if page fails to load or elements missing | Windows 10/11, Chrome, Firefox, Edge | Hemant Bhase | TBD | No risk | Vaishali Sonanis
3 | Cart Page | - Product details (name, price, description) shown | Coupon entry, shipping options, bulk updates | Automation Testing (Selenium + TestNG) | Pass if cart shows correct products, allows quantity and removal, and 'Checkout'/'Continue Shopping' work as intended | Testing paused if cart does not load or products/actions missing | Windows 10/11, Chrome, Firefox, Edge | Hemant Bhase | TBD | No risk | Vaishali Sonanis
- Quantity displayed and updated
- Remove button
- Cart badge updates
- Continue Shopping button
- Checkout button